## Tracking Log
Item | Counterparty/Jurisdiction | Category | Status | Requested Date | Follow-Up Date | Responsible | Notes
Delaware Good Standing Certificate | State of Delaware | Good Standing | Complete (12/12) | 2025-12-01 |  | Quentin Sarr | Certificate received and filed to closing set.
Ohio Good Standing Certificate | State of Ohio | Good Standing | Outstanding | 2025-12-02 | 2025-12-15 | Quentin Sarr | Chasing Dov at client for confirmation of filing agent submission.
Odell Estoppel Certificate | Odell (Landlord) | Estoppel | Outstanding | 2025-12-03 | 2025-12-16 | Quentin Sarr | Sent draft estoppel form to counterparty counsel; awaiting execution.
Whitfield Estoppel Certificate | Whitfield (Landlord) | Estoppel | Outstanding | 2025-12-03 | 2025-12-16 | Quentin Sarr | No response yet to initial request; second follow-up sent 12/10.