## Closing Checklist
Item | Entity | Category | Status | Owner | Notes | Date Completed
Delaware good standing certificate | Sandhurst Holdings, Inc. | Good Standing | Complete | Quentin Sarr | Certificate obtained and confirmed current as of 12/12 | 2025-12-12
Ohio good standing certificate | Sandhurst Operating Co. | Good Standing | Outstanding | Quentin Sarr | Flagged at deal status meeting; need to confirm OH filing status before closing
Odell estoppel certificate | Odell Properties LLC (landlord) | Estoppel Certificate | Outstanding | Quentin Sarr | Escalated to client contact; awaiting countersignature
Whitfield estoppel certificate | Whitfield Realty Trust (landlord) | Estoppel Certificate | Outstanding | Quentin Sarr | Escalated to Ingrid Solheim per email thread "Re: Whitfield Estoppel - Escalating to Client"; landlord unresponsive, considering client-side escalation
UCC lien searches - Delaware | Sandhurst Holdings, Inc. | Lien Search | Complete | Quentin Sarr | No liens of record outside permitted financing | 2025-12-10
UCC lien searches - Ohio | Sandhurst Operating Co. | Lien Search | Complete | Quentin Sarr | No liens of record outside permitted financing | 2025-12-10
Material contracts consent requirements | Sandhurst Operating Co. | Contracts | In Progress | Quentin Sarr | Two vendor agreements require consent to assignment; requests sent
Officer/director closing certificates | Sandhurst Holdings, Inc. | Closing Deliverable | Not Started | Quentin Sarr | Draft forms to be circulated once good standing items clear
Payoff letters - existing lender | Sandhurst Operating Co. | Financing | In Progress | Quentin Sarr | Awaiting updated payoff figure from lender