## Closing Checklist
Item # | Item | Responsible Party | Status | Due Date | Notes
1 | Estoppel certificates - all leased locations | Landlord counsel / Quentin Sarr | Outstanding | TBD | 3 of 7 returned; remaining outreach stalled on Odell/Whitfield landlord contact - Quentin unable to reach by phone (voicemails left); escalated to counsel per Dov's request, no callback received yet as of latest check-in
2 | Good standing certificates - Target and subsidiaries | Quentin Sarr | In progress | TBD | Ordered from Secretary of State; DE and OH pending; Delaware still pending direct follow-up
3 | Payoff letters - existing credit facility | Borrower's counsel | Outstanding | TBD | Follow up with lender counsel re: per diem calc
4 | UCC lien searches - Target and subsidiaries | Quentin Sarr | Complete |  | Filed and reviewed; no unexpected liens
5 | Board resolutions - Target approving transaction | Target's counsel | Complete |  | Executed copies received
6 | Stockholder written consent | Target's counsel | Complete |  | Executed and on file
7 | Disclosure schedule - final bring-down | Quentin Sarr / deal team | In progress | TBD | Awaiting updates from management re: material contracts section
8 | Third-party consents - material contracts | Quentin Sarr | Outstanding | TBD | 5 of 12 consents received; 2 require fee payments; status unchanged since last team check per Ingrid
9 | Employment agreements - key employees | HR counsel | In progress | TBD | 2 of 4 executed
10 | Escrow agreement - execution | All parties | Outstanding | TBD | Draft circulated; comments due from escrow agent
11 | Financing certificates and closing deliverables | Lender's counsel | Outstanding | TBD | Coordinate with credit agreement covenant workstream
12 | Officer's certificate - Target | Quentin Sarr | Not started | TBD
13 | Wire instructions - all parties confirmed | Quentin Sarr | Not started | TBD | Confirm with closing agent 24 hrs prior
14 | Closing set assembly and distribution | Quentin Sarr | Not started | TBD | To be finalized post-signing
15 | MIP figure cross-check against closing checklist | Quentin Sarr / Mira | Blocked | TBD | Blocked pending supplier counterclaim file from Dov/Samir; file holder still unidentified as of latest update, being chased by Dov with ~1 hour turnaround expected; EOD deadline today remains in effect; no movement since last check-in with Ingrid