## Recut Discrepancies
Item # | Document / Folder | Data Room Version | Timestamp Flagged | Issue Description | Raised By | Escalated (Y/N) | Status | Follow-Up Owner | Notes
1 | Sandhurst Platform - Financials Folder | Recut v3 | 09:15 | Version uploaded at 09:15 does not match version uploaded at 09:28 for same folder index; file names identical but contents differ (Q3 trial balance figures changed). | Quentin Sarr | Y | Escalated to deal team | Ingrid Solheim | Discrepancy confirmed independently by I. Solheim and M. Chandrasekhar in deal status meeting.
2 | Sandhurst Platform - Financials Folder | Recut v3 (09:28 version) | 09:28 | Later upload appears to correct several line items without a change log or notice to counsel; unclear whether this reflects a management restatement or an upload error. | Quentin Sarr | Y | Escalated to deal team | Ingrid Solheim | Need confirmation from Sandhurst counsel on which version is authoritative.
3 |  |  |  | Review of remaining recut folders for similar 09:15/09:28 pattern completed following deal status meeting; no additional folders showed the same dual-timestamp discrepancy. | Quentin Sarr | N | Closed - no further instances found | Quentin Sarr | Reviewed all Sandhurst Platform recut folders as of today; Financials Folder remains the only affected item. Findings shared with deal team.
4 |  |  |  | Pending: request clean version history / audit trail from data room administrator. |  | N | Open - awaiting response | Mira Chandrasekhar | Raised again in today's deal status meeting; Mira confirmed follow-up with data room admin still pending, no audit trail received as of this update.
5 |  |  |  | Verification check: confirmed doc-000225 (signature pages tracker, saved yesterday) is tied to closing mechanics / Section I closure sign-off (Hyunwoo, Ingrid, Petra), not to the recut/data room timestamp discrepancies tracked here. | Quentin Sarr | N | Closed - no linkage found | Quentin Sarr | No changes made to Items 1-4 as a result of this check; noted for traceability per current plan block instruction to verify doc-000225's ties.
6 | Whitfield/Sandhurst MIP Mechanics |  |  | Open question: awaiting confirmation from Dov on holder ID(s) relevant to MIP mechanics; deadline letter has been drafted and sent to Whitfield per Ingrid Solheim. Three chases sent to Dov with no response received. Holder ID confirmation may affect closing mechanics timeline. | Quentin Sarr | Y | Escalated - no response after three chases | Quentin Sarr | Discussed in today's deal status meeting; still no response from Dov as of meeting. Ingrid Solheim confirmed escalation authorized given lack of response.
7 | Whitfield/Sandhurst - Deal Status Meeting Follow-Up |  |  | Deal status meeting held today (6 turns) covering Whitfield/Sandhurst escalation status and MIP mechanics; recut discrepancy (Items 1-2) and audit trail request (Item 4) both discussed and status confirmed unchanged/pending as reflected above. No new open items identified beyond those already tracked. | Quentin Sarr | N | Closed - meeting notes incorporated | Quentin Sarr | Added for traceability; consolidates meeting outcomes into existing tracker items rather than creating duplicate entries.
8 | Whitfield/Sandhurst MIP Mechanics - Escalation Above Dov |  |  | Following three unanswered chases to Dov, escalated matter per Ingrid Solheim's direction by looping in Dov's supervisor/counsel to obtain holder ID confirmation needed for MIP mechanics. | Quentin Sarr | Y | Open - awaiting response from Dov's supervisor/counsel | Quentin Sarr | Escalation initiated same day as deal status meeting; supersedes prior 'awaiting response from Dov' status in Item 6. Will update once supervisor/counsel responds.