## Open Items
Item # | Workstream | Description | Jurisdiction | Owner | Status | Escalation | Next Step | Due Date
1 | Regulatory | Confirm antitrust filing thresholds for target's EU subsidiaries | EU | Quentin Sarr | Open | No | Awaiting local counsel confirmation | 2025-06-20
2 | Regulatory | Whitfield export control clearance - target's licensing arrangements | UK | Samir Bhatt | Escalated | Yes - chasing Whitfield directly | Follow up call scheduled with Whitfield counsel | 2025-06-18
3 | Corporate | Review target's cap table for outstanding option grants | US - Delaware | Mira Chandrasekhar | In Progress | No | Reconcile against latest 409A valuation | 2025-06-19
4 | Commercial | Assess change-of-control provisions in top 10 customer contracts | US | Mira Chandrasekhar | In Progress | No | Draft summary memo for deal team | 2025-06-22
5 | IP | Confirm chain of title on core platform patents | US / EU | Quentin Sarr | Open | No | Awaiting assignment records from target | 2025-06-21
6 | Employment | Review key employee retention agreements | US | Mira Chandrasekhar | Not Started | No | Schedule kickoff with HR diligence team | 2025-06-25
7 | Regulatory | Second jurisdiction filing question - clarify with Samir | TBD - pending Samir/Quentin call | Quentin Sarr | Open | No | Circling back per chat with Samir | 2025-06-19
8 | Litigation | Confirm no pending litigation disclosed in data room matches public record search | US | Mira Chandrasekhar | In Progress | No | Cross-check against Sandhurst add-on findings (tkt-000011) | 2025-06-20

## Escalation Log
Date Raised | Item # | Raised By | Escalated To | Summary | Resolution Status
2025-06-16 | 2 | Samir Bhatt | Whitfield (opposing counsel/regulator contact) | Chasing Whitfield on export control clearance timeline; no response yet | Open - Samir monitoring
2025-06-17 | 7 | Quentin Sarr | Samir Bhatt | Circling back on outstanding jurisdictional question from prior call | Open - awaiting Samir's reply