## Estoppel Tracker
Counterparty | Property/Lease Reference | Estoppel Requested | Date Sent | Status | Last Contact | Outstanding Item | Follow-Up Owner | Follow-Up Deadline | Closing Risk
Odell | Sandhurst - Odell Lease (Site 2) | Yes | 2024-05-20 | Outstanding | Ingrid Solheim - no response as of last check | Signed estoppel certificate not yet returned | Ingrid Solheim | 2024-06-04 | High - blocking closing
Whitfield | Sandhurst - Whitfield Lease (Site 4) | Yes | 2024-05-20 | Outstanding - attempted callback | Quentin Sarr - phone attempt unsuccessful, left voicemail | Signed estoppel certificate not yet returned; callback pending | Quentin Sarr | 2024-06-04 | High - blocking closing
Marsh & Cole (landlord counsel, other sites) | Sandhurst - remaining 6 leases | Yes | 2024-05-15 | Received | N/A | None | Mira Chandrasekhar | Complete | None

## Action Log
Date | Action | Taken By | Notes
2024-05-30 | Status call - deal team | Dov Reinhardt | Confirmed Odell/Whitfield are the two open items blocking closing
2024-05-30 | Checked status with Ingrid | Ingrid Solheim | No update from Odell since prior check
2024-05-30 | Attempted call to Quentin re: Whitfield | Quentin Sarr | Neither party answered; voicemail left
2024-05-30 | Instructed 1-hour callback window or escalate | Dov Reinhardt | If no callback within the hour, team to escalate directly to counterparty
2024-05-30 | Directed next step given voicemails | Mira Chandrasekhar | Recommended direct outreach to Samir per voicemail follow-up