## Slide 1: Employment Matters — Board Update
Prepared for the Board / Compensation & Personnel Committee
Presented by Fionnuala Doherty, Partner, Employment
Status as of today — draft for discussion
Notes: Opening slide. Frame this as a status update across three active matters: the staff complaint, the reduction in force, and the pending litigation moving toward mediation. Emphasize that none of these currently requires Board action, but the Board should be aware.
[REVIEW — T. Mokoena, Docket]: No dated deadlines attach to this slide. Sign-off: OK as is.

## Slide 2: Matter 1: Staff Complaint — Status
Complaint raised by a staff member; Harriet Lindqvist is the client contact managing day-to-day handling
Fact-finding was paused on receipt to allow written direction of counsel to issue before any investigative steps were taken
Written direction of counsel is now in place — this preserves privilege over the investigation and any resulting report
Fairness commitments have been set for both the complainant and the subject of the complaint
Guidance given on how to respond to the complainant's confidentiality question
Conclusion: no deadline currently requires Board disclosure at this stage
Notes: Key point for the Board: without a written direction from counsel before fact-finding starts, the investigation record is discoverable. That direction is now in place, so we're on the right footing. This is a contemporaneous update, not a forward-looking plan — the call with Harriet has already happened and outcomes are settled. Reassure the Board that escalation triggers are being watched but none have been hit yet.
[REVIEW — T. Mokoena, Docket]: 'Written direction of counsel is now in place' has no execution date logged against the matter calendar — flagging for confirmation of the date so it can be docketed. 'Conclusion: no deadline currently requires Board disclosure at this stage' is accurate as a docket-driven statement (no deadline compels disclosure); this is not a legal conclusion about whether disclosure is otherwise advisable, and should not be read as one. Sign-off pending date confirmation on written direction.
[REVIEW — follow-up, T. Mokoena]: Per today's docket call, still no firm date on file for the written direction of counsel. Evidence remains thin on timing — requesting the execution date be sent over so this can be closed out. Holding sign-off on this bullet only; remainder of slide's factual narrative is not in dispute.

## Slide 3: Matter 2: Sable Ridge Reduction in Force
Position Statement on proposed RIF approach has been prepared and is under review
Selection criteria have been sharpened to address adverse impact analysis and cross-check requirements
Risk mitigation steps now expressly tie into investigation privilege posture
Any RIF-adjacent complaint requiring fact-finding will be opened under written direction of counsel, consistent with firm standard practice
No open issues currently require Board sign-off
Notes: This slide should reassure the committee that the RIF selection methodology has been legally reviewed for defensibility and that we've built in the same privilege safeguard used on the staff complaint matter — if a complaint arises out of the RIF, we won't let fact-finding get ahead of counsel's written direction.
[REVIEW — T. Mokoena, Docket]: 'Under review' has no target completion date on the docket. Flagging — please confirm a review-completion date so it can be calendared and tracked against any RIF notice deadline. 'No open issues currently require Board sign-off' is supported only insofar as no dated deadline currently triggers sign-off; tightened understanding accordingly. Sign-off pending review-completion date.
[REVIEW — follow-up, T. Mokoena]: Chat confirmation received from R. Duchamp on Sable Ridge coordination, but that confirms staffing/coordination only — it is not a review-completion date and does not resolve the open flag above. Still awaiting a firm date for the Position Statement review before this bullet can be signed off.
[REVIEW — additional, T. Mokoena, Docket]: Separately, per chat exchange with R. Duchamp, the choice-of-law enforceability question flagged by H. Bae has been closed out on her end and confirmed clear to close by me — that item does not carry an open deadline and requires no calendaring. Noting this resolves the item raised in my prior cross-slide query below; it is unrelated to the Position Statement review-completion date, which remains open.
[REVIEW — additional, T. Mokoena, Docket]: Per chat with L. Abara, Sable Ridge is no longer unresourced/unowned on the docket side — noting this as a staffing/ownership update only, distinct from the Position Statement review-completion date, which remains the sole outstanding item for sign-off on this slide. A separate calendar entry has also been opened at L. Abara's request regarding a duplicate docket call on this matter; that entry is administrative (deduplication of calendar invites) and does not itself carry a deadline requiring Board notice.
[REVIEW — additional, T. Mokoena, Docket]: Per today's docket-call planning, the rotating note-taker fix is confirmed in effect, and the duplicate-call deduplication process flagged by L. Abara is holding as intended. Both are process/administrative confirmations only, carry no deadline, and do not touch the Position Statement review-completion date, which remains the sole outstanding item for sign-off on this slide.

## Slide 4: Matter 3: Pending Litigation — Path to Mediation
Plaintiff's counsel has been engaged regarding mediation scheduling
Internal call scheduled (tomorrow after 2:00 PM or Thursday before 11:00 AM) to cover:
– Exposure analysis
– Settlement authority
– A related personnel-side question
Mediation dates will be proposed to plaintiff's counsel following that call
Roland has been asked to confirm attendee availability and provide any case updates in advance
Notes: Do not discuss specific settlement range in this deck — that's reserved for the live call with Roland and the team. The Board update should convey that a process is underway and disciplined, not the numbers themselves.
[REVIEW — T. Mokoena, Docket]: Internal call window (tomorrow after 2:00 PM or Thursday before 11:00 AM) is not yet fixed to a single date/time on the docket — flagging until confirmed, since mediation-date proposals and any related deadlines cascade from it. Roland's confirmation of attendee availability is also outstanding. 'Mediation dates will be proposed... following that call' is a planned next step, not yet a docketed deadline — noting the distinction. Sign-off pending firm date.
[REVIEW — follow-up, T. Mokoena]: As of today's docket call, the call window remains a two-option window rather than a confirmed single date/time, and Roland's availability confirmation is still outstanding. Evidence is too thin to calendar a days-remaining count against 'mediation dates will be proposed.' Requesting the firm date be locked and circulated so this cascades properly onto the docket. Sign-off withheld pending firm date.

## Slide 5: Cross-Matter Note: Privilege Discipline
Firm standard practice: every internal investigation is opened under a written direction from counsel
Without that direction, the investigation report is discoverable — this is being applied consistently across the staff complaint and any RIF-adjacent complaints
This is a deliberate, firm-wide safeguard, not a one-off precaution for this matter
Notes: This slide exists because people often don't realize this is the baseline practice, not an exception. Worth stating plainly to the Board so they understand why timing on fact-finding sometimes appears to pause before it starts.
[REVIEW — T. Mokoena, Docket]: Policy statement, no deadline attached. Sign-off: OK as is.

## Slide 6: Next Steps
Staff complaint: monitor investigation progress; no further Board input needed at this time
RIF: finalize Position Statement review; confirm selection criteria sign-off
Litigation: hold internal call this week; propose mediation dates to plaintiff's counsel thereafter
Will circulate a further update once mediation dates are confirmed or if any matter requires Board attention
Notes: Close by reinforcing that nothing here currently requires a Board vote or formal action — this is a status and awareness update. Invite questions. Call me if easier.
[REVIEW — T. Mokoena, Docket]: 'Finalize Position Statement review' and 'hold internal call this week' both lack calendared target dates. Requesting firm dates for each so they can be docketed with days-remaining tracking. 'Staff complaint: no further Board input needed at this time' is consistent with the docket record showing no pending deadline; flagging only that this should be revisited once the written-direction date above is confirmed. Sign-off pending those dates.
[REVIEW — follow-up, T. Mokoena]: Same three open items discussed on today's docket call remain unresolved — written direction date (Matter 1), Position Statement review-completion date (Matter 2), and internal call date/time plus Roland's availability (Matter 3). None have a firm date yet, so none of these Next Steps items can be calendared with a days-remaining figure. Sign-off withheld on the RIF and litigation bullets pending dates; staff-complaint bullet sign-off pending written-direction date per Matter 1 note; closing bullet is fine as a general commitment and does not require a date.
[REVIEW — additional, T. Mokoena, Docket]: Update to prior note — the choice-of-law enforceability question flagged by H. Bae has now been confirmed closed via chat with R. Duchamp; it does not belong on this matter list and no date is required. The three open items above (written-direction date, review-completion date, internal call date/Roland's availability) remain the only outstanding calendar items on this deck. Also noting per L. Abara: Sable Ridge staffing/ownership is resolved (no longer unresourced), and a separate calendar entry has been created to track the duplicate docket call issue he flagged — neither of these adds a new deadline to this list.
[REVIEW — additional, T. Mokoena, Docket]: Per today's docket-call planning, confirming the rotating note-taker fix is in effect and the duplicate-call deduplication process is holding as intended — both administrative confirmations only, no deadline attached, no change to the three open items still requiring firm dates before sign-off.