## Docket
Deadline | Description | Owner | Days Remaining | Status | Source | Notes
2025-06-02 | Conditional certification opposition brief due | M. Reyes | 12 | Open | Court order dated 2025-05-05 | Response to plaintiffs' motion for conditional certification; filing must be PDF upon service
2025-06-09 | Reply in support of motion to compel arbitration (subset of drivers) | J. Alvarez | 14 | Open | Local rule 7.1 briefing schedule | Pryor calc confirmed correct per B. Ashworth/T. Mokoena chat; filed Thursday, due a week from Monday off filing date; 14 days remaining per docket practice; reconfirmed with Hyun-woo and restated in EOD reminder; Lucien reviewed Jan 16 corrected Master Docket Report as accurate, no further action needed
2025-06-16 | Deadline to serve initial written discovery responses | M. Reyes | 26 | Open | Rule 33/34 - 30 day clock from service on 2025-05-17 | Discovery requests served by plaintiffs 2025-05-17; duplicate-call process and rotating note-taking confirmed holding on both sides per docket call
2025-06-23 | Deadline to identify opt-in notice recipients (if certification granted) | J. Alvarez | 33 | Contingent | Court order dated 2025-05-05 | Contingent on ruling; tracked pending outcome of certification briefing
2025-07-07 | Expert disclosure deadline - damages model | K. Whitfield | 47 | Open | Scheduling order dated 2025-04-01 | Damages model build not yet started per last status check
2025-05-30 | Corrective action: To/CC read-aloud fix (Sable Ridge docket call) | T. Mokoena | 0 | Resolved | Docket call outcome - internal process fix | Distinct corrective action from note-taker rotation fix; addresses To/CC read-aloud error flagged on Sable Ridge duplicate call invite issue raised by L. Abara; confirmed to Lucien as a separate calendar entry from the note-taker rotation fix, with escalation to admin/IT for the duplicate-call recurring-invite issue; same-day deadline noted and closed
2025-05-30 | Corrective action: rotating note-taker fix (Sable Ridge docket call) | T. Mokoena | 0 | Resolved | Docket call outcome - internal process fix | Distinct corrective action from To/CC read-aloud fix; confirmed in effect per today's docket call; duplicate-call deduplication process (raised by L. Abara re: Sable Ridge) holding as intended; administrative/process confirmation only, no new deadline created; does not resolve the unidentified docket entry item below
2025-05-31 | Sable Ridge Position Statement review - completion date | Jamal | 1 | Open | Docket call outcome - ownership and completion date confirmed by Jamal | Ownership previously unresolved; Hyun-woo, Lucien, and Rosalie each confirmed not owner; escalated to Bennett; Jamal has confirmed ownership and set completion date at EOD tomorrow; sign-off on review approach separately resolved - Bennett determined Jamal self-approves, closing the second-reviewer/sign-off question after Hyun-woo disclaimed ownership of that call and Rosalie disclaimed the second-reviewer question; this closes out the last unresolved Sable Ridge item
2025-05-30 | Confirm owner/matter for unidentified docket entry (doc-000030) or pull it | Unassigned - pending Lucien | 0 | Open - unresolved as of 15:30 save | Docket call/chat escalation - manual entry, no date or matter code on record | Substantive update at 15:30 save, not a duplicate: entry remains unowned. Bennett, Hyun-woo, Jamal, and Lucien have each disclaimed ownership; Rosalie has ruled out Sable Ridge as the matter and pointed to Lucien's related-party conflicts memo as the likely owning matter; Lucien has been pressed repeatedly for a firm yes/no on that link and has not yet confirmed or denied. Placeholder row retained per Klara's suggestion to keep a durable record until an owner and matter are confirmed. Standing deadline: today, EOD, 0 days remaining - confirm the tie to the related-party conflicts memo or the entry gets pulled.