## Master Docket
Deadline | Event / Filing | Court / Authority | Days Remaining | Owner | Status | Notes
2025-06-02 | Opposition to Motion for Conditional Certification due | N.D. Cal. | 7 | M. Ferris | Open | Draft in review with partner; needs final cite-check
2025-06-09 | Reply ISO Motion to Compel Arbitration due | N.D. Cal. | 14 | R. Okafor | Open | Awaiting client declaration
2025-06-16 | Deadline to serve supplemental discovery responses (Set 3) | N.D. Cal. | 21 | M. Ferris | At risk | Owner has not confirmed receipt of documents from client
2025-06-23 | Deposition of named plaintiff J. Alvarez | N.D. Cal. | 28 | R. Okafor | Open | Location and court reporter confirmed
2025-07-07 | Close of pre-certification discovery | N.D. Cal. | 42 | M. Ferris | Open | No extensions anticipated
2025-07-21 | Joint case management statement due | N.D. Cal. | 56 | R. Okafor | Open | Template to be circulated 2 weeks prior
2025-08-04 | Hearing on Motion for Conditional Certification | N.D. Cal. | 70 | M. Ferris | Open | Calendar hold confirmed with courtroom deputy

## Escalations
Deadline | Event / Filing | Owner | Days Remaining | Escalation Sent | Escalated To | Response Received
2025-06-16 | Deadline to serve supplemental discovery responses (Set 3) | M. Ferris | 21 | Yes - 2025-05-26 | Supervising Partner | No