## Review Status
Batch ID | Custodian | Document Count | Review Status | Reviewer | Privilege Calls | Responsive Calls | QC Complete | Notes
BATCH-014 | M. Alvarez (Regional Dispatch) | 1240 | Complete | N. Haddad | 12 | 340 | Yes | Final version confirmed against production set 3/14
BATCH-015 | M. Alvarez (Regional Dispatch) | 980 | Complete | N. Haddad | 8 | 275 | Yes | Final version confirmed against production set 3/14
BATCH-016 | T. Bishop (Fleet Ops) | 1560 | In Progress | N. Haddad | 5 | 190 | No | Second-pass QC pending; 22 docs flagged for privilege re-review — Rosalie Duchamp confirmed all 22 as privileged (in-house counsel cc'd in forwarded chain); privilege log to be updated before QC closes
BATCH-017 | T. Bishop (Fleet Ops) | 1105 | Not Started | Unassigned | 0 | 0 | No | Awaiting reviewer assignment — escalated again this week to Rosalie Duchamp as an end-of-day open item; no reviewer identified yet; timeline risk persists
BATCH-018 | R. Okafor (HR/Payroll) | 875 | In Progress | N. Haddad | 3 | 410 | No | Meal-break policy docs concentrated here; prioritizing — first pass on this custodian now roughly two-thirds complete
BATCH-019 | R. Okafor (HR/Payroll) | 690 | Complete | N. Haddad | 4 | 220 | Yes | Final version confirmed against production set 3/12
BATCH-020 | Corporate Timekeeping System Export | 2210 | In Progress | N. Haddad | 0 | 605 | No | Voluminous; timekeeping logs — sampling protocol applied per team discussion; sample results consistent so far, no expansion of sample needed at this time

## Open Issues
Issue | Batch(es) Affected | Raised By | Status | Notes
Final-version confirmation mismatch on BATCH-014/015 vs. review platform tag | BATCH-014, BATCH-015 | N. Haddad | Resolved | Confirmed platform tags updated to reflect final versions; no substantive re-review needed
Privilege re-review needed on 22 documents | BATCH-016 | N. Haddad | Resolved | Rosalie Duchamp confirmed all 22 documents (forwarded emails with in-house counsel cc'd late in chain) as privileged; privilege log update in progress before QC closes
Reviewer capacity gap | BATCH-017 | N. Haddad | Open | Still no reviewer assigned; flagged to Rosalie Duchamp again as an end-of-day open item — will affect production timeline if not staffed