## Review Tracker
Batch ID | Custodian | Source | Date Range | Docs in Batch | Reviewed | Remaining | Responsive | Privileged | Reviewer | Status | Notes
B-001 | M. Alvarez (Dispatch Manager) | Email - O365 | 2022-01-01 to 2024-12-31 | 1840 | 1840 | 0 | 312 | 14 | K. Torres | Complete | Privilege log entries drafted. Reviewer sign-off: batch complete, figures reconcile with privilege log (14 entries) - no further action. For the file. [N. Haddad: concur - counts tie out, sign-off stands.] [P. Kovacs: concur - reconciles to Privilege Log Summary (14 entries, M. Alvarez). Sign-off stands. For the file.]
B-002 | R. Okafor (Regional Ops Director) | Email - O365 | 2022-01-01 to 2024-12-31 | 2210 | 2210 | 0 | 401 | 22 | K. Torres | Complete | 2 docs flagged for partner review - potential common-interest issue. Reviewer note: 'potential' issue is not yet confirmed - recommend stating basis for common-interest concern or downgrading language until partner review occurs. For the file. [N. Haddad: agree with reviewer note as written - this may be nothing, but I'd also ask that the 2 flagged docs be identified by Bates/ID here so partner review isn't searching the full batch. Am I wrong to want that logged before we call this Complete?] [P. Kovacs: agree with N. Haddad - Bates/ID for the 2 flagged docs should be logged in this row before Complete stands as final. Recommend downgrading 'Complete' to 'Complete - pending partner review of 2 flagged docs' until IDs are added and partner has weighed in. This also ties to the Privilege Log Summary entry for Regional Managers noting the same common-interest scope question - the two should be resolved together. For the file.]
B-003 | Fleet Timekeeping System Export | Structured data - CSV | 2022-01-01 to 2024-12-31 | 1 | 1 | 0 | 1 | 0 | H. Bae | Complete | Converted to workpaper for expert; see damages model. Reviewer sign-off: single-document batch, disposition clear - no further action. [N. Haddad: this may be nothing, but the sign-off asserts the conversion happened without naming the damages model file or date it was received - recommend adding that cross-reference so the disposition is checkable, not just asserted.] [P. Kovacs: agree with N. Haddad - sign-off should not stand on an unnamed cross-reference. Requesting the specific damages model file name/version and receipt date from H. Bae before this row is treated as closed. Holding sign-off pending that addition. For the file.]
B-004 | T. Nasser (HR Director) | Email - O365 | 2021-06-01 to 2024-12-31 | 1975 | 1580 | 395 | 288 | 31 | J. Park | In progress | Behind pace; second reviewer added this week. Reviewer note: 'behind pace' asserted but no target date or comparison rate shown in this row - recommend adding the pace benchmark being missed so status is verifiable at next check-in. For the file. [N. Haddad: agree - concur with existing reviewer note, nothing to add.] [P. Kovacs: concur with N. Haddad and the existing reviewer note - benchmark still needed at next check-in. No further note. Final: second-reviewer staffing addition this week is noted and adequate as a mitigation step, but does not itself substitute for the missing benchmark - that requirement stands until added. For the file.]
B-005 | Driver Handbook & Policy Files | Shared drive | 2019-01-01 to 2024-12-31 | 64 | 64 | 0 | 64 | 3 | H. Bae | Complete | Includes 6 handbook revisions - meal-break policy language changed 2021-03. Meal-break liability flag (N. Haddad) logged here per agreed approach - no escalation; issue is blocked pending transcript, being tracked, not a new review item. Reviewer sign-off: batch complete, tracking approach consistent with agreed handling - no further action. [N. Haddad: this may be nothing, but since this is my own flag, I'd rather not be the one signing off on how it's tracked - recommend the row name the specific transcript we're waiting on so 'blocked pending transcript' is verifiable and not just my earlier note restated. Am I off base flagging my own entry here?] [P. Kovacs: not off base - agree a second reviewer should confirm this rather than the flag's author. As reviewer of record: the transcript being awaited should be named here (deponent and date, if set) before 'blocked pending transcript' is treated as verified. Document-batch disposition (64/64 reviewed, 3 privileged, logged) is otherwise sound and sign-off on that count stands; the tracking-language question stays open until the transcript is named. For the file.]
B-006 | Regional Managers (5 custodians) | Email - O365 | 2022-01-01 to 2024-12-31 | 6340 | 3100 | 3240 | 890 | 58 | J. Park / K. Torres | In progress | Largest batch; on track for review complete by next Friday per current pace. Reviewer note: with 3,240 of 6,340 docs remaining (roughly half), 'on track' is not supported by the numbers shown alone - recommend adding the daily/weekly review rate used to project the Friday date. For the file. [N. Haddad: concur with reviewer note - the arithmetic here doesn't support 'on track' as stated, this should stay open until the rate is added.] [P. Kovacs: concur - agree this stays open. 'On track' should be replaced with the actual projection basis (docs/day rate x remaining days) before next Friday is repeated as a target. Flagging for J. Park / K. Torres at next check-in. For the file.]
B-007 | Text messages - company-issued phones (12 drivers named in complaint) | Mobile extraction | 2022-06-01 to 2024-12-31 | 940 | 210 | 730 | 40 | 1 | H. Bae | In progress | Vendor extraction delayed 9 days; escalated to IT vendor, resolved. Reviewer note: 'resolved' should be confirmed against vendor correspondence before this is treated as closed, given 730 docs remain unreviewed. For the file. [N. Haddad: agree - concur with existing reviewer note, nothing to add.] [P. Kovacs: concur - 'resolved' refers to the extraction delay only, not the batch, and should be confirmed against vendor correspondence as N. Haddad notes. 730 of 940 remain unreviewed; batch status of 'In progress' is accurate and stands. For the file.]
B-008 | Payroll/Timekeeping Correspondence - Finance | Email - O365 | 2022-01-01 to 2024-12-31 | 512 | 0 | 512 | 0 | 0 | Unassigned | Not started | Needs reviewer assignment; flag for staffing at Thursday check-in. Reviewer sign-off: status accurately reflects no work performed - no further note needed. [N. Haddad: concur - sign-off stands.] [P. Kovacs: concur - 0 of 512 reviewed matches 'Not started' exactly. Sign-off stands. For the file.]

## Privilege Log Summary
Log Entry Count | Custodian | Basis Asserted | Status
14 | M. Alvarez | Attorney-client - counsel advice re: meal-break policy revision | Finalized
22 | R. Okafor | Attorney-client / work product - litigation hold and investigation comms | Finalized
3 | Driver Handbook & Policy Files | Work product - draft policy language reviewed by counsel | Finalized
58 | Regional Managers (5) | Attorney-client - mixed; 6 entries pending partner review for common-interest scope | Draft - pending partner sign-off [N. Haddad: this may be nothing, but 'pending partner sign-off' has no date attached - recommend adding when partner review is expected so this doesn't sit open indefinitely alongside the B-002 flag above, which raises the same common-interest question.] [P. Kovacs: agree with N. Haddad - no target date currently attached. Recommend requesting a date from the assigned partner and linking resolution of these 6 entries to the 2 flagged docs in B-002, since both raise the same common-interest scope question and should not be decided separately. Status remains Draft pending that.]
1 | Text messages | Attorney-client - single message forwarded to counsel | Finalized

## Status Rollup
Metric | Value
Total documents identified | 13882
Total reviewed to date | 9005
Percent reviewed
Total responsive | 1996
Total privileged (logged) | 129
Batches not started | 1
Batches at risk of missing review-complete target | 3 [N. Haddad: this may be nothing, but B-004, B-006, and B-007 each carry an open reviewer note questioning pace, projection, or resolution status - recommend this count reflect those three rather than just one, or explain here why they're excluded.] [P. Kovacs: agree with N. Haddad - as reviewer of record, the count of 1 is not supported by the open notes in the tracker. B-004 (pace benchmark undefined), B-006 (arithmetic contradicts 'on track'), and B-007 ('resolved' unconfirmed against vendor correspondence, 730 docs remaining) are all open. Updated this figure to 3 to match the tracker. Sign-off stands on this metric as corrected; underlying B-004/B-006/B-007 notes remain open in their own rows. For the file. [P. Kovacs - final: reviewed as reviewer of record. The corrected count of 3 is fully supported by the tracker's own open notes (B-004, B-006, B-007) and no fourth batch qualifies on the current record. Sign-off on this metric stands as final; resolution of the underlying pace/projection/vendor-confirmation questions remains tracked separately in each batch's row. For the file.]
Target review-complete date | 2025-04-18