## Filing Status
Item | Court/Forum | Document | Due Date | Status | Responsible | Filing Method | Notes
1 | N.D. Cal. | Opposition to Motion to Compel Arbitration | 2025-06-18 | On track - final review | Hyunwoo Bae | ECF | Position Statement draft confirmed with Jamal; finalizing citations - Bennett to confirm sign-off ownership (Jamal self-signing, no second reviewer)
2 | N.D. Cal. | Joint Case Management Statement | 2025-06-20 | Drafting - awaiting client input on class figures | Bennett Ashworth | ECF | Noor flagged mismatch in meal-break count figures - resolving before filing
3 | N.D. Cal. | Notice of Related Cases | 2025-06-19 | Filed | Rosalie Duchamp | ECF | Confirmed filed today, clean
4 | N.D. Cal. | Reply in Support of Conditional Certification | 2025-06-25 | Not started - waiting on opposition response | Hyunwoo Bae | ECF | Will not get filed today; opposition not yet due
5 | N.D. Cal. | Declaration of Records Custodian | 2025-06-20 | Signature still pending end of day | Rosalie Duchamp | ECF | Chasing signature from client HR contact; carrying forward to tomorrow
6 | N.D. Cal. | Proposed Order re: Case Management Statement | 2025-06-20 | Drafting | Bennett Ashworth | ECF | Depends on item 2 figures being finalized
7 | N.D. Cal. | Stipulation Extending Time to Respond | 2025-06-17 | Filed | Rosalie Duchamp | ECF | Confirmed on docket 06/17 AM
8 | Secretary of State (corporate filing) | Ardmore Elevator Good Standing Request | 2025-06-17 | MISSED - 4pm clerk cutoff passed, no confirmed owner | Unassigned - escalated to Ingrid, Samir, Lucien, Thandiwe; Bennett still needs to name an owner | Clerk filing counter | 4pm clerk cutoff (not midnight) missed with no owner named despite 3:30 checkpoint push for a direct yes/no from Ingrid and Samir; Thandiwe confirmed today's chase referenced this same Ardmore Elevator good-standing request and asked for the actual deadline after the miss - clarified cutoff already passed; contrast with still-stalled Whitfield chase; logged for tomorrow's docket call prep

## Overnight Docket Activity
Date/Time | Court | Docket Entry | Description | Action Needed | Owner
2025-06-17 22:14 | N.D. Cal. | Dkt. 87 | Order setting hearing on Motion to Compel Arbitration for 2025-07-10 | Hearing calendared; Hyunwoo and client notified | Rosalie Duchamp
2025-06-17 23:02 | N.D. Cal. | Dkt. 88 | Defendant's Notice of Appearance - new counsel added | Service list updated; Bennett to confirm resolution on record | Rosalie Duchamp