# Updated Fee Estimate – Sandhurst / Odell-Whitfield Closing

Prepared for Imelda Frost ahead of the board call. This estimate reflects status as of tonight, including the still-unconfirmed Odell/Whitfield ancillary docs split and the estoppel count now tracking to 4/14. Quentin did not return tonight's requested confirmation on either item; the ask has been reset to first thing tomorrow morning. Samir has confirmed the checklist side of the split.

## Basis for Estimate

Odell/Whitfield ancillary documents split: single-owner split endorsed (Samir on checklist, Quentin on Odell/Whitfield); Samir's side confirmed, Quentin's confirmation now expected tomorrow morning after no callback tonight.

Good standing certificate: complete (11/12 items on checklist).

Estoppel certificates: 2 outstanding of original count, tracking to 4/14; count unchanged, pending Quentin's firm ETA tomorrow morning.

Closing checklist: reviewer notes appended without rewriting existing sign-offs; no signature page circulates until every condition precedent carries an owner's initials - hard gate, not a scheduling preference.

Target closing: this quarter, contingent on the split resolving and the estoppel count confirming as firm, not aspirational; firm numbers now expected from Quentin tomorrow morning.

## Fee Estimate by Workstream

| Workstream | Status | Est. Hours to Complete | Est. Fees |
| --- | --- | --- | --- |
| Closing checklist / conditions precedent tracking | In progress - Samir confirmed | 16 | $12,800 |
| Estoppel certificates (2 outstanding) | In progress, targeting 4/14, count unchanged | 10 | $7,200 |
| Odell/Whitfield ancillary docs split | Awaiting Quentin's firm confirmation tomorrow AM | 8 | $6,400 |
| Good standing certification | Complete | 0 | $0 |
| Closing set preparation and signature page assembly | Not started - gated on CP initials | 12 | $9,600 |
| General deal management / escalation calls | Ongoing - includes tonight's follow-up and reset ask to Quentin | 7 | $5,600 |

## Total Estimated Fees to Close

$41,600, assuming no further slippage on the estoppel count or reopening of the ancillary docs split. Each week of delay on either item adds an estimated $3,500-$5,000 in incremental fees from repeated escalation calls and checklist re-review. Tonight's non-response from Quentin has not yet been booked as slippage, but if tomorrow morning's confirmation also slips, expect the low end of that range to apply.

## Risk to Estimate

Quentin did not return tonight's requested firm split confirmation and estoppel count; the ask has been reset to first thing tomorrow morning. If that also slips, timeline and fee estimate both move.

4/14 estoppel target is not yet firm; being presented internally as targeting, not committed, until Quentin's count is confirmed.

No signature page will circulate until every condition precedent has an owner's initials on the checklist - this is a hard gate, not a scheduling preference.

Unrelated: no impact expected on this estimate from the separate supplier counterclaim decision (holding position, no filing) or the Ardmore elevator acquisition timeline.