# Closing Checklist Status Report — Sandhurst Platform Acquisition

This report summarizes the current status of open closing checklist items as of today, following today's Corporate deal status call, for the deal team's reference. One item remains open; three items have closed since the last update.

## Closed Since Last Update

Secretary's Certificate — closed. Signer confirmation and execution timing were tracked with Quentin and have been resolved.

Delaware good standing certificate (Sandhurst Real Estate Holdco LLC) — closed. 12 of 12 certificates now in hand; escalation to Whitfield's counsel resolved the last outstanding jurisdiction. Confirmed to Dov, Samir, and Ingrid. See Memorandum — Delaware Good Standing Certificate Follow-Up (Sandhurst Real Estate Holdco LLC) for background.

Item #10 — MIP mechanics ratchet fix — closed. Independently confirmed by both Quentin Sarr and Samir Bhatt; see Changelog below.

## Open Items

| Item | Status | Owner | Notes |
| --- | --- | --- | --- |
| Odell/Whitfield estoppel certificates | 2 of 3 received; escalated to Whitfield's counsel; pending callback | Quentin (owner, closeout) | Mira has confirmed Quentin owns closing out this item. Escalation trigger has passed; no callback received yet despite outreach. Ancillary docs/staffing split also remains open pending this callback. This is now the sole remaining item blocking the signature page. |
| APA drafting notes (Articles 4–7) | Updated; under review | Ingrid (reviewer) | Drafting notes in Sections 4.1, 6.2, and 7.1 have been revised to reflect that Delaware good standing is now fully closed (12 of 12 certificates in hand); Secretary's Certificate signer resolution noted accordingly. Section 4.3 and the status note updated to retain the Odell/Whitfield estoppel as the sole remaining open item, with ownership reflected as Quentin's and noting Mira is no longer directly chasing it. Per Ingrid's go-ahead, substantive drafting has advanced elsewhere: Section 7.1 proposes a 5-business-day standard for the good standing certificate day count, and a new Section 4.5 (Employee Matters) representation on wage-and-hour disclosure has been added, consistent with ongoing diligence tracking. Mira is holding off on further edits pending Ingrid's review of the Articles 4-7 redline. |

## Notes

Checklist is otherwise clean apart from the Odell/Whitfield estoppel item; reaffirmed to Dov, Samir, and Quentin that the checklist stays open and no signature page goes out until that item is resolved.

MIP figures cross-check remains a separate open blocker: per team norm, this cannot be treated as resolved until Whitfield/Sandhurst confirm receipt of the corrected figures; that thread remains Quentin's to close out. This is distinct from Item #10 (MIP mechanics ratchet fix), which is now closed.

## Changelog

Item #10 (MIP mechanics ratchet fix) — closed. Independently confirmed by Quentin Sarr and Samir Bhatt.