## Closing Checklist
Row | Item | Status | Owner | Reviewer Notes | Sign-off / Hold Flag
1 | Certificate of Formation / Good Standing (Seller) | Hold | S. Bhatt | No change from prior review; hold flag unchanged pending updated bring-down. | Hold
2 | Certificate of Formation / Good Standing (Target) | Hold | S. Bhatt | No change from prior review; hold flag unchanged pending updated bring-down. | Hold
3 | Third-Party Consents — Landlord (Odell/Whitfield lease) | Hold | Q. Sarr | No change from prior review; testing/evidence unchanged since last version. | Hold
4 | Corporate Authorizations — Board Resolutions | Complete | M. (Mira) | Prior sign-off stands; no new information. | Signed off
5 | UCC Lien Searches | Hold | S. Bhatt | Updated this revision: per S. Bhatt's check-in, good standing tracking is 11 of 12 items back, one jurisdiction still outstanding; hold flag remains in place pending that final confirmation. | Hold
6 | Officer's Certificate | Complete | M. (Mira) | Prior sign-off stands; no new information. | Signed off
7 | Retention Agreements — Key Employees | Hold | S. Bhatt | No change from prior review; hold flag unchanged. | Hold
8 | Estoppel Certificates — Odell/Whitfield (Landlord) | Open — Escalated | Q. Sarr | Updated this revision: following direct escalation and final pre-meeting push to Odell and Whitfield (cc Dov Reinhardt and Samir Bhatt) demanding a firm, dated commitment on the two outstanding estoppel certificates, Ingrid Solheim confirmed via chat that one of the two outstanding certificates is now closed out, which Quentin has acknowledged and confirmed back to Ingrid. This narrows the outstanding count to one certificate still open, partially reconciling the prior discrepancy between Samir's '1 of 3 back' count and Mira's differing count; concrete confirmation (which cert, when) has now been obtained for the closed-out item, but the remaining certificate's status and a firm dated commitment are still outstanding. Quentin's open question — whether the two Michael Odell references from the past two days are the same person — remains unresolved and outreach continues on that basis. | Open — reviewer flag, not signed off
9 | Lien Payoff Letters | Hold | S. Bhatt | No change from prior review; outstanding per prior notes. | Hold
10 | HSR Threshold Confirmation | Open — Insufficient Information | S. Bhatt | Per S. Bhatt's check-in this revision: checklist unchanged, good standing 11 of 12 items stable with one jurisdiction still outstanding; HSR threshold confirmation remains insufficient pending full resolution of Row 8 estoppel status, which has now partially resolved (one of two certificates closed out) but is not yet complete. | Open — reviewer flag
11 | Disclosure Schedules — Bring-down | Complete | M. (Mira) | Prior sign-off stands; no new information. | Signed off
12 | IP Assignment Confirmations | Complete | M. (Mira) | Prior sign-off stands; no new information. | Signed off
13 | Ancillary Documents / Checklist Staffing Split | Open — Insufficient Information | Q. Sarr / S. Bhatt | Updated this revision: staffing split remains unconfirmed (still 'N') as confirmed to Dov Reinhardt before the 09:15 meeting and again before the board call. Direct escalation and final pre-meeting push sent to Odell and Whitfield demanding a firm answer on the staffing split, cc'ing Dov and Samir, but no firm answer has been received as of this revision. Separately, Quentin confirmed with Mira the Secretary's Certificate signer question, which does not resolve the staffing split but has been closed out as a related item. Remains unresolved pending staffing decision. | Open — reviewer flag
14 | Officer and Director Questionnaires | Complete | M. (Mira) | Prior sign-off stands; no new information. | Signed off