## Signature Pages Tracker
Party | Document | Signatory | Status | Date Received | Held By | Notes
Sandhurst Platform Holdings, Inc. | Purchase Agreement | M. Whitfield, CEO | Collected | 2024-06-03 | Q. Sarr | Original received; scanned copy on file
Sandhurst Platform Holdings, Inc. | Disclosure Schedule Certificate | M. Whitfield, CEO | Collected | 2024-06-03 | Q. Sarr
Buyer — Kestrel Acquisition Vehicle LLC | Purchase Agreement | R. Okonkwo, Managing Member | Collected | 2024-06-04 | Q. Sarr
Buyer — Kestrel Acquisition Vehicle LLC | Assignment and Assumption Agreement | R. Okonkwo, Managing Member | Collected | 2024-06-04 | Q. Sarr
Escrow Agent — Danforth Trust Co. | Escrow Agreement | L. Danforth, VP | Collected | 2024-06-04 | Q. Sarr
Landlord — Whitfield Properties LLC | Tenant Estoppel Certificate | M. Whitfield, Manager | Outstanding |  | Q. Sarr | Escalated to deal team after three consecutive days of no response from Whitfield or counsel, per escalation trigger; awaiting direction on next steps
Supplier Counterclaim Party (unidentified) | Release / Settlement Signature Page | TBD | Outstanding |  | Dov / Samir | Signature page cannot be prepared until underlying supplier counterclaim file and holder ID are received from Dov; one-hour window elapsed, re-chased directly, no holder ID resolution yet as of latest follow-up
MIP Participants (schedule pending) | MIP Acknowledgment Signature Pages | TBD | Outstanding |  | Mira | Blocked on MIP figure cross-check against closing checklist, pending supplier counterclaim file; MIP receipt confirmation to Samir/Ingrid remains outstanding
Sandhurst Platform Holdings, Inc. | Secretary's Certificate (Delaware Good Standing attached) | J. Alvarez, Secretary | Outstanding |  | Q. Sarr | Delaware good standing certificate still pending direct follow-up
Guarantor — Whitfield Family Trust | Guaranty Agreement | M. Whitfield, Trustee | Collected | 2024-06-05 | Q. Sarr
Title Company — Meridian Title & Escrow | Title Affidavit | S. Park, Escrow Officer | Collected | 2024-06-05 | Q. Sarr
Lender — Braxton Capital Partners | Payoff Letter Acknowledgment | T. Braxton, Managing Director | Collected | 2024-06-05 | Q. Sarr

## Summary
Metric | Count
Total signature pages tracked | 12
Collected | 8
Outstanding | 4
Outstanding — blocked on external file/data | 2
Outstanding — awaiting counsel/counterparty response | 1
Outstanding — awaiting internal follow-up | 1
Section I — Status | Closed out; sign-off received from Hyunwoo, Ingrid, and Petra
Email Policy Note | Read-aloud To/CC policy is now standing and applicable to all outgoing emails on this matter