## Slide 1: Ardmore Elevator Acquisition — Fee Estimate Update
Prepared for board call — current status and revised fee-to-close estimate
Closing target: this quarter, pending single outstanding condition
Notes: Level-set slide. Emphasize this is an update, not a re-scope — underlying deal structure unchanged.

## Slide 2: Closing Status
Only open closing condition: Whitfield estoppel certificate
Deadline letter issued; escalated directly to Whitfield's counsel
Firm closing date to be set within 2 business days of Whitfield's response
All other conditions precedent cleared: good standing (12/12), MIP ratchet fix (Item #10) closed pending Saoirse sign-off
Checklist remains marked Outstanding until certificate is actually received — no signature page circulates before then
Notes: Hold the line here if asked why checklist isn't 'green' — condition isn't satisfied until certificate in hand.

## Slide 3: Fee Estimate — Revised Basis
Estimate reflects extended timeline risk from Whitfield delay and additional MIP mechanic testing
MIP ratchet fix validated against sponsor illustrative MOIC scenarios (1.0x–3.0x) — no discontinuities or overpayment; work is complete, not open-ended
Environmental exposure (Terminal 7) cost figures unchanged from prior sign-off — this update adds severity context only, not new cost
Work Stream | Prior Estimate | Revised Estimate | Basis for Change
Deal Team — Diligence & Negotiation | $410,000 | $410,000 | Complete; no change
MIP Ratchet Mechanic Review & Testing | $35,000 | $48,000 | Added scenario testing across 5 MOIC cases (1.0x–3.0x) at sponsor's request
Closing Conditions / Estoppel Follow-Up | $20,000 | $42,000 | Extended counsel escalation, deadline letter, direct outreach to Whitfield's counsel
Environmental (Terminal 7) Workpaper Support | $60,000 | $68,000 | Severity assessment added to existing exposure workpaper; dollar figures unchanged
Closing Mechanics & Signature Set | $25,000 | $25,000 | Unchanged; held pending estoppel receipt
Contingency — Timeline Slippage Beyond Quarter-End | $0 | $30,000 | New line; reflects risk if Whitfield does not respond within 2-business-day window
Total | $550,000 | $623,000 | 
Notes: Walk the board through the delta line by line if asked — the $73k increase is almost entirely Whitfield escalation and MIP testing, not scope creep.

## Slide 4: Environmental Exposure (Terminal 7) — Cost & Severity
Underlying exposure cost figures are final per prior sign-off — no change this update
New severity assessment added to workpaper to directly address board's question on how serious the exposure is, not just its cost
Source Notes updated to reflect workpaper now covers both cost and severity
Notes: This slide answers Imelda's standing question — lead with severity framing, not just the dollar figure, since that's what was asked.

## Slide 5: Next Steps
Dov to call Whitfield's counsel directly to demand estoppel certificate as sole open condition, quarter-end timing at risk
Quentin to follow up escalation in writing same day
Firm closing date confirmed within 2 business days of Whitfield's response
Checklist status corrected to Closed only upon actual receipt of certificate
Revised fee estimate above assumes resolution within this window; further delay will require another update
Notes: If board pushes on timeline certainty, be direct: we don't have a firm date until Whitfield responds, and we're not pretending otherwise.