## Deal Points
# | Issue | Buyer Position | Seller Position | Status | Owner | Target Resolution Date
1 | Purchase price adjustment mechanism | Working capital true-up at close + 60-day true-up | Fixed price, no true-up | Resolved - working capital true-up at close + 45-day true-up (compromise) | D. Reinhardt | 2025-04-10
2 | Escrow amount | 10% of purchase price, 18-month survival | 5% of purchase price, 12-month survival | Resolved - 7.5% of purchase price, 15-month survival | D. Reinhardt | 2025-04-08
3 | Grain inventory valuation method | Independent inspector at close, FIFO costing | Seller's book value at close | Open - seller pushing back on inspector cost allocation; call scheduled | Associate - Diligence | 2025-04-09
4 | Elevator facility environmental indemnity | Uncapped for known Ardmore soil issue | Capped at escrow amount | Open - awaiting Phase II lab results before further negotiation | D. Reinhardt | 2025-04-11
5 | Non-compete radius for seller principals | 75 miles / 5 years | 25 miles / 3 years | Resolved - 50 miles / 4 years | D. Reinhardt | 2025-03-28
6 | Assignment of grain storage leases | Consent required from three counterparties | Automatic assignment clause | Resolved - consent required, two of three consents in hand | Associate - Diligence | 2025-04-07
7 | Employee retention / key manager agreements | Retention agreements for 2 elevator managers | No retention requirement | Resolved - both signed | D. Reinhardt | 2025-04-01
8 | Financing contingency | None - all cash close | None - all cash close | Resolved | D. Reinhardt | 2025-03-20

## Closing Checklist
Item | Responsible Party | Status | Due Date | Notes
Definitive Purchase Agreement - final markup | D. Reinhardt | In progress | 2025-04-10 | Escrow and price adjustment terms resolved; incorporating into next markup
Disclosure schedules - seller delivery | Seller's counsel | In progress | 2025-04-05 | Partial delivery received; remaining schedules promised by 2025-04-07
Environmental Phase II report - Ardmore site | Third-party consultant | In progress | 2025-04-08 | Soil sampling results expected this week
Grain storage lease consents (3 counterparties) | Associate - Diligence | In progress | 2025-04-07 | Two consents received; third pending
Financing payoff letters | Buyer's lender | Not started | 2025-04-12
Key manager retention agreements - execution | D. Reinhardt / HR | Complete | 2025-04-01 | Both managers signed
Title commitment - elevator real property | Title company | Received | 2025-03-25 | No exceptions requiring resolution
Regulatory filings - state grain warehouse license transfer | Associate - Diligence | Not started | 2025-04-15
Escrow agreement - final draft | D. Reinhardt | In progress | 2025-04-09 | Terms resolved (7.5% / 15-month); drafting underway
Closing date confirmation to client | D. Reinhardt | Open | 2025-04-03 | Imelda Frost requesting firm closing date - target 2025-04-18 to be confirmed; provisional date given, contingent on clearing outstanding conditions below
Good standing certificates - buyer and seller entities | Associate - Diligence | In progress | 2025-04-09 | Samir/Ingrid confirmed final count: 1 entity still outstanding - owner to initial checklist once received
Landlord/counterparty estoppels | Associate - Diligence | Open | 2025-04-14 | Samir/Ingrid confirmed final count: 2 estoppels outstanding, both must close today - matches Gideon's flagged rates table item
Signature pages - buyer | D. Reinhardt | Not started | 2025-04-16 | Will not circulate until all conditions precedent have owner's initials on checklist
Signature pages - seller | Seller's counsel | Not started | 2025-04-16
Wire instructions confirmation | Buyer's controller | Not started | 2025-04-16

## Proposed Timeline
Milestone | Target Date | Dependency
Resolve remaining open deal points #3-4 | 2025-04-11 | Phase II results; follow-up call with seller's counsel on inspection costs
Disclosure schedules finalized | 2025-04-12 | Remaining seller delivery + buyer review
Environmental Phase II final report | 2025-04-12 | Consultant lab results
Final DPA and escrow agreement execution-ready | 2025-04-15 | Deal points #3-4 resolved
Lease consents complete (all 3) | 2025-04-14 | Third counterparty response
Entity good standing certificates complete | 2025-04-12 | 1 outstanding entity cert - owner TBD
Estoppels complete (2 outstanding) | 2025-04-14 | Both must close today per Samir/Ingrid
Target closing date | 2025-04-18 | All above items complete