## Engagement Calendar
Engagement | Client | Audit Type | Year-End | Planning | Fieldwork Start | Fieldwork End | Review/Issuance | Lead | Status
Fairmount Community Foundation — FS | Fairmount Community Foundation | Financial Statement Audit | 2025-12-31 | 2025-10-15 | 2025-11-03 | 2025-12-08 | 2025-12-20 | TBD | Planning
Fairmount Community Foundation — Single Audit | Fairmount Community Foundation | Single Audit (Uniform Guidance) | 2025-12-31 | 2025-10-15 | 2025-12-09 | 2026-01-15 | 2026-01-31 | TBD | Planning
Rivergate Housing Trust — FS & Single Audit | Rivergate Housing Trust | Financial Statement & Single Audit | 2025-12-31 | 2025-11-01 | 2025-12-01 | 2026-01-20 | 2026-02-10 | TBD | Planning
Kestrel Manufacturing 401(k) — Plan Audit | Kestrel Manufacturing | Plan Year 2025 Audit | 2025-12-31 | 2025-09-15 | 2025-11-10 | 2025-12-15 | 2026-01-10 | TBD | Fieldwork In Progress
Cardinal Ridge Builders — FS | Cardinal Ridge Builders | Financial Statement Audit | 2025-12-31 | 2025-11-01 | 2025-12-01 | 2026-01-15 | 2026-02-05 | TBD | Planning
Harbor Light Distribution — FS | Harbor Light Distribution | Financial Statement Audit | 2025-12-31 | 2025-10-01 | 2025-11-17 | 2025-12-20 | 2026-01-10 | Imogen Carraway | Fieldwork In Progress
Ashfield Pension Trust — FS | Ashfield Pension Trust | Financial Statement Audit | 2025-12-31 | 2025-10-01 | 2025-11-10 | 2025-12-18 | 2026-01-15 | TBD | Planning
Stonebridge Property Group — FS | Stonebridge Property Group | Financial Statement Audit | 2025-12-31 | 2025-11-01 | 2025-12-08 | 2026-01-25 | 2026-02-15 | TBD | Planning
Meridian Family Health — Review | Meridian Family Health | Compilation Review | 2025-12-31 | 2025-11-15 | 2026-01-05 | 2026-01-30 | 2026-02-10 | TBD | Planning
Northwind Software — Quality of Earnings | Northwind Software | QoE Engagement | 2025-12-31 | 2025-10-20 | 2025-11-17 | 2026-01-05 | 2026-01-20 | TBD | Fieldwork In Progress

## PBC Tracking
Client | Category | Item | Due From Client | Received | Locked | Notes
Harbor Light Distribution | Financial Records | General Ledger & Trial Balance | 2025-11-03 | 2025-11-10 | 2025-11-12 | Locked for Wed 14:30 review
Harbor Light Distribution | Financial Records | Accounts Receivable Aging & Testing | 2025-11-03 | 2025-11-10 | 2025-11-12 | Locked for Wed 14:30 review
Harbor Light Distribution | Financial Records | Testing Files & Workpapers | 2025-11-10 | 2025-11-17 | 2025-11-17 | Locked for fieldwork
Kestrel Manufacturing 401(k) | Plan Documents | K-1s & Posting Summary | 2025-10-31 | 2025-11-07 | 2025-11-07 | Locked for review
Kestrel Manufacturing 401(k) | Financial Records | Plan Census & Benefit Schedules | 2025-10-31 | 2025-11-07 | 2025-11-07 | Locked
Northwind Software | Financial Records | Screenshot & Concrete Analysis | 2025-10-31 | In Progress | Pending | ETA: post-IT gate Wed morning
Northwind Software | Payroll | Payroll Records | 2025-10-31 | 2025-11-10 | 2025-11-10 | Locked for QoE testing
Fairmount Community Foundation | Grants & Compliance | Federal Award & Grant Detail | 2025-11-15 | Pending | Pending | For Single Audit component
Rivergate Housing Trust | HUD Records | HUD Submission & Reconciliation | 2025-11-30 | Pending | Pending | Due during fieldwork phase
Cardinal Ridge Builders | Contract Documents | Construction Contracts & Change Orders | 2025-11-30 | Pending | Pending | For revenue testing

## Team Capacity
Team Member | Current Assignment | Utilization | Next Available | Notes
Imogen Carraway | Harbor Light Distribution — Engagement Lead | 80% | 2026-01-15 | Post-issuance pivot to calendar planning
Theo Brandt | Harbor Light Distribution — Senior | 85% | 2025-12-22 | Testing files finalized
Priscilla Wong | Harbor Light Distribution — Senior | 85% | 2025-12-22 | AR/GL locked, ready for Wed review
Victor Alade | Harbor Light Distribution & Northwind — Senior | 90% | 2025-12-20 | Leading AR/GL sync & QoE gaps pair
Raj Malhotra | Northwind Software — Senior | 95% | 2026-01-10 | QoE lead; concrete analysis post-IT gate
Rosalind Calder | Northwind Software — Staff | 80% | 2025-12-15 | QoE support & screenshot verification
Owen Castile | Northwind Software — Staff | 75% | 2025-12-10 | QoE testing & workpaper support
Freya Holt | Multiple — Scheduler | 70% | Ongoing | Coordinating AR/GL sync & IT gate timing
Lucia Mendes | Kestrel Manufacturing — Staff | 60% | 2025-12-31 | K-1 and posting summary review complete
Nadia Osman | Kestrel & Summit — Staff | 65% | 2026-01-05 | Plan census locked

## Critical Path & Blockers
Engagement | Critical Item | Current Status | Blocker? | Resolution / Owner | Target Date
Northwind Software | Screenshot & Concrete Analysis | In Progress — IT gate pending | Yes | Raj — post-Wed morning IT gate; Elias to support | 2025-11-19
Harbor Light Distribution | AR/GL Review & Sign-Off | Locked Wed 14:30 | No | Victor leading; same-day feedback | 2025-11-12
Harbor Light Distribution | Three Flags Walk & Testing Buttoning | Scheduled 15:00 | No | Victor + Gaps Pair (Desmond & Maya) | 2025-11-12
Kestrel Manufacturing 401(k) | Plan Census & Benefit Certification | Locked | No | Lucia & Nadia; posting summary complete | 2025-11-07
Fairmount Community Foundation | Single Audit Grant Detail | Pending client submission | Likely | Imogen to follow up post-Harbor Light | 2025-12-01