## K-1 Prep
Partner Entity | Tax ID | Return Due Date | K-1 Data Locked | Schedule M-1 Reconciled | Basis Calculation | Guaranteed Payments Verified | Capital Account Activity | Related-Party Transactions | Status | Owner | Notes
Stonebridge Property Group LP | XX-XXXXXXX | 2026-03-15 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | In Progress | Lucia Mendes | GL access locked Wed 14:30; AR/October detail confirmed
Stonebridge Real Estate Holdings | XX-XXXXXXX | 2026-04-15 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | Pending | Lucia Mendes | Real Estate owned by Lucia; docs pulling
Riverside Investment Partners | XX-XXXXXXX | 2026-03-15 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | Pending | Desmond Ortiz | All locked per Desmond for Wed 14:30
Hartwell Development Co. | XX-XXXXXXX | 2026-04-15 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | Pending | Desmond Ortiz | All locked per Desmond for Wed 14:30

## Data Feeds
Feed | Source | Format | Last Received | Owner | Locked | Notes
GL Export | Client accounting system | CSV | 2025-01-13 | Raj Malhotra | TRUE | GL access clear on Raj's end; locked Wed 14:30
AR Detail — October | Accounts Receivable subledger | CSV | 2025-01-13 | Gabriel Fontes / Maya Lindqvist | TRUE | $47K confirmed AR/October per Idris; detail locked
Payroll Reconciliation | Payroll system | XLSX | 2025-01-13 | Sylvia Nakamura | TRUE | 401(k) allocation reconciled; GL access locked payroll side
AP Aging | Accounts Payable subledger | CSV | Pending | Desmond Ortiz | FALSE | AP/May reconciliation in progress per Gabriel
PBC List | Client | Email | 2025-01-13 | Theo Brandt | TRUE | All set for Wed 14:30

## Timeline
Date | Milestone | Owner | Status
2025-01-13 | Data feeds locked; Stonebridge kickoff meeting | Lucia Mendes | Complete
2025-01-15 | Client conference — GL review, scope confirmation | Lucia Mendes | Scheduled
2025-01-22 | K-1 draft schedules; partner allocations | Lucia Mendes | In Progress
2025-02-12 | K-1 returns filed (Q1 partners) | Lucia Mendes | Pending
2025-03-15 | Partnership returns due | Lucia Mendes | Pending