## Audit Schedule
Engagement | Client | Audit Type | Fieldwork Start | Fieldwork End | Target Sign-Off | Manager | Status
tkt-000001 | Fairmount Community Foundation | Financial Statement Audit | 2025-02-03 | 2025-02-28 | 2025-03-21 | Imogen Carraway | Planning
tkt-000002 | Fairmount Community Foundation | Single Audit (Uniform Guidance) | 2025-03-03 | 2025-03-28 | 2025-04-18 | Imogen Carraway | Planning
tkt-000003 | Rivergate Housing Trust | Financial Statement & Single Audit | 2025-02-10 | 2025-03-07 | 2025-03-28 | Imogen Carraway | Planning
tkt-000004 | Kestrel Manufacturing 401(k) | Plan Year 2025 Audit | 2025-02-17 | 2025-03-14 | 2025-04-04 | Imogen Carraway | In Progress
tkt-000005 | Cardinal Ridge Builders | Financial Statement Audit | 2025-02-24 | 2025-03-21 | 2025-04-11 | Imogen Carraway | Planning
tkt-000007 | Harbor Light Distribution | Financial Statement Audit | 2025-01-20 | 2025-02-14 | 2025-03-07 | Imogen Carraway | Fieldwork
tkt-000009 | Stonebridge Property Group | Financial Statement Audit | 2025-03-03 | 2025-03-28 | 2025-04-18 | Imogen Carraway | Planning
tkt-000010 | Ashfield Pension Trust | Financial Statement Audit | 2025-03-10 | 2025-04-04 | 2025-04-25 | Imogen Carraway | Planning
tkt-000008 | Meridian Family Health | Review (Non-Audit) | 2025-04-07 | 2025-04-25 | 2025-05-16 | Imogen Carraway | Planning

## PBC & Lock Points – Kestrel 401
Workstream | Owner | Lock Target | Status | Notes
GL Reconciliation | Colin MacKey | 2025-03-05 14:30 | On Track | GL sync scheduled Wed 14:30; AR locked
Payroll & 401(k) Reconciliation | Raj Malhotra | 2025-03-05 10:30 | Locked | Logs pulled, sign-off ready
Loop & Ladder Testing | Maya Lindqvist / Theo Brandt | 2025-03-06 10:30 | Locked | Thursday confirmed; no reschedules
Quality of Earnings | Victor Alade / Gabriel Fontes | 2025-03-07 EOD | Locked | Friday solid; no cascade risk
Recordkeeper Data Cascade | Imogen Carraway | 2025-03-10 | Confirmed | All team lockpoints in; cascade clear

## Outstanding PBC by Engagement
Engagement | Client | Item | Due from Client | Due Date | Received | Status
tkt-000007 | Harbor Light Distribution | FY2025 General Ledger (trial balance) | Harbor Light Finance | 2025-01-31 | TRUE | Ready
tkt-000007 | Harbor Light Distribution | Bank reconciliations (all accounts) | Harbor Light Finance | 2025-01-31 | TRUE | Ready
tkt-000007 | Harbor Light Distribution | Accounts receivable aging & confirmation list | Harbor Light Finance | 2025-02-07 | FALSE | Pending
tkt-000004 | Kestrel Manufacturing 401(k) | Plan investment schedule & holdings report | Plan Recordkeeper | 2025-02-14 | FALSE | Pending
tkt-000004 | Kestrel Manufacturing 401(k) | Participant census & distribution history | Plan Administrator | 2025-02-14 | FALSE | Pending
tkt-000001 | Fairmount Community Foundation | FY2025 General Ledger & trial balance | Fairmount Finance | 2025-02-21 | FALSE | Not Yet Due
tkt-000001 | Fairmount Community Foundation | Grant ledgers & restricted fund schedules | Fairmount Finance | 2025-02-21 | FALSE | Not Yet Due

## Risk Watch
Engagement | Risk Area | Mitigation | Owner | Next Check-In
tkt-000004 | Recordkeeper data cascade—confirmations not yet in | All upstream lockpoints confirmed; cascade clears 2025-03-10; follow up Thu AM if needed | Imogen Carraway | 2025-03-06
tkt-000007 | Harbor Light AR aging still pending; fieldwork in progress | Follow up by Wed EOD; confirm receipt and readiness for in-field verification | Imogen Carraway | 2025-02-05
tkt-000002 | Fairmount Single Audit—federal spend threshold documentation | Awaiting Elias Finch's summary; threshold review documented separately | Imogen Carraway | 2025-02-12